## Sheet1
Activity ID | Activity Name | Original Duration | Start | Finish
Procurement, Design & Development |  | 463 | 2025-09-29 | 2027-01-05
Procurement Part-1 (Order Finalisation) |  | 183 | 2025-09-30 | 2026-03-31
Support System |  | 125 | 2025-09-30 | 2026-02-27
MEP-PR1-SUP1000 | PROC- ORDER FIN - Electrical - Supports including Siesmic Supports | 25 | 2025-09-30 | 2025-10-30
MEP-PR1-SUP1015 | PROC- ORDER FIN - ELV & BMS- Supports including Siesmic Supports | 20 | 2025-12-17 | 2026-01-10
MEP-PR1-SUP1010 | PROC- ORDER FIN - FPS- Supports including Siesmic Supports | 20 | 2025-11-24 | 2025-12-16
MEP-PR1-SUP1025 | PROC- ORDER FIN - HSD- Supports including Siesmic Supports | 20 | 2026-02-05 | 2026-02-27
MEP-PR1-SUP1005 | PROC- ORDER FIN - HVAC - Supports including Siesmic Supports | 20 | 2025-10-31 | 2025-11-22
MEP-PR1-SUP1020 | PROC- ORDER FIN - PHE- Supports including Siesmic Supports | 20 | 2026-01-12 | 2026-02-04
Electrical |  | 125 | 2025-09-30 | 2026-02-27
Priority 1 |  | 125 | 2025-09-30 | 2026-02-27
MEP-PR1-ELE-1020 | PROC- ORDER FIN - ELE - Busduct | 10 | 2025-12-05 | 2025-12-16
MEP-PR1-ELE-1000 | PROC- ORDER FIN - ELE - Conduits | 10 | 2025-11-12 | 2025-11-22
MEP-PR1-ELE-1035 | PROC- ORDER FIN - ELE - Earthing & Lightning Protection | 10 | 2026-01-12 | 2026-01-22
MEP-PR1-ELE-1100 | PROC- ORDER FIN - ELE - HT & LT Power Cables | 10 | 2025-11-24 | 2025-12-04
MEP-PR1-ELE-1010 | PROC- ORDER FIN - ELE - Isolation Transformer (For Lighting & ELV System) | 10 | 2025-12-30 | 2026-01-10
MEP-PR1-ELE-1050 | PROC- ORDER FIN - ELE - N2 Generator | 10 | 2025-10-18 | 2025-10-30
MEP-PR1-ELE-1065 | PROC- ORDER FIN - ELE - Power Transformer | 10 | 2025-10-31 | 2025-11-11
MEP-PR1-ELE-1040 | PROC- ORDER FIN - ELE - RMU | 10 | 2026-01-23 | 2026-02-04
MEP-PR1-ELE-1060 | PROC- ORDER FIN - ELE - Substation automation system | 10 | 2026-02-17 | 2026-02-27
MEP-PR1-ELE-1025 | PROC- ORDER FIN - ELE - Switch & Sockets | 10 | 2025-12-17 | 2025-12-29
MEP-PR1-ELE-1045 | PROC- ORDER FIN - ELE - UPS | 10 | 2026-02-05 | 2026-02-16
MEP-PR1-ELE-1115 | PROC- ORDER FIN - ELE - Wires & Cables (HT & LT) | 15 | 2025-09-30 | 2025-10-17
Priority 2 |  | 10 | 2025-10-18 | 2025-10-30
MEP-PR1-ELE-1005 | PROC- ORDER FIN - ELE - Cable Tray | 10 | 2025-10-18 | 2025-10-30
MEP-PR1-ELE-1030 | PROC- ORDER FIN - ELE - Distribution Boards | 10 | 2025-10-18 | 2025-10-30
Priority 3 |  | 62 | 2025-10-18 | 2025-12-31
MEP-PR1-ELE-1131 | PROC- ORDER FIN - ELE - Elevators | 30 | 2025-11-26 | 2025-12-31
MEP-PR1-ELE-1015 | PROC- ORDER FIN - ELE - External & Internal Light Fixtures | 12 | 2025-10-18 | 2025-11-01
MEP-PR1-ELE-1055 | PROC- ORDER FIN - ELE - Light Pole | 10 | 2025-11-03 | 2025-11-13
MEP-PR1-ELE-1120 | PROC- ORDER FIN - ELE - Load Bank | 10 | 2025-11-14 | 2025-11-25
HVAC |  | 81 | 2025-09-30 | 2026-01-06
Priority 1 |  | 42 | 2025-09-30 | 2025-11-19
MEP-PR1-HVAC-1050 | PROC- ORDER FIN - HVAC - Automatic Balancing Valve | 6 | 2025-10-13 | 2025-10-18
MEP-PR1-HVAC-1035 | PROC- ORDER FIN - HVAC - Buffer Tanks | 12 | 2025-09-30 | 2025-10-14
MEP-PR1-HVAC-1040 | PROC- ORDER FIN - HVAC - Degasser System (Expansion Tank,Pressurisation unit with Vaccuum Degasser) | 12 | 2025-09-30 | 2025-10-14
MEP-PR1-HVAC-1085 | PROC- ORDER FIN - HVAC - DX AHU's & TFA's | 10 | 2025-10-17 | 2025-10-29
MEP-PR1-HVAC-1020 | PROC- ORDER FIN - HVAC - Gauges & Accessories | 6 | 2025-10-13 | 2025-10-18
MEP-PR1-HVAC-1010 | PROC- ORDER FIN - HVAC - Motorised Valves | 4 | 2025-10-13 | 2025-10-16
MEP-PR1-HVAC-1090 | PROC- ORDER FIN - HVAC - Pressurisation Fans | 10 | 2025-10-17 | 2025-10-29
MEP-PR1-HVAC-1045 | PROC- ORDER FIN - HVAC - Two Way On/Off Valve | 6 | 2025-10-13 | 2025-10-18
MEP-PR1-HVAC-1005 | PROC- ORDER FIN - HVAC - Valves (Manual Butterfly Valve & NRV) | 4 | 2025-10-13 | 2025-10-16
MEP-PR1-HVAC-1030 | PROC- ORDER FIN - HVAC - VRF System | 18 | 2025-10-30 | 2025-11-19
Priority 2 |  | 81 | 2025-09-30 | 2026-01-06
MEP-PR1-HVAC-1065 | PROC- ORDER FIN - HVAC - ADP's (Diffusers,Grilles, VCD & Fire Dampers) | 8 | 2025-10-08 | 2025-10-16
MEP-PR1-HVAC-1075 | PROC- ORDER FIN - HVAC - Chemical Dosing System | 26 | 2025-10-17 | 2025-11-17
MEP-PR1-HVAC-1100 | PROC- ORDER FIN - HVAC - Fire Rated Ducts | 15 | 2025-12-18 | 2026-01-06
MEP-PR1-HVAC-1070 | PROC- ORDER FIN - HVAC - Flexible Ducts | 26 | 2025-11-18 | 2025-12-17
MEP-PR1-HVAC-1060 | PROC- ORDER FIN - HVAC - GI Ducts | 6 | 2025-09-30 | 2025-10-07
MEP-PR1-HVAC-1000 | PROC- ORDER FIN - HVAC - MS Pipes | 10 | 2025-09-30 | 2025-10-11
MEP-PR1-HVAC-1025 | PROC- ORDER FIN - HVAC - Rubber Bellows | 10 | 2025-10-13 | 2025-10-24
MEP-PR1-HVAC-1080 | PROC- ORDER FIN - HVAC - Side Stream Filter | 15 | 2025-10-17 | 2025-11-04
MEP-PR1-HVAC-1015 | PROC- ORDER FIN - HVAC - Strainers | 10 | 2025-10-13 | 2025-10-24
Priority 3 |  | 6 | 2025-10-13 | 2025-10-18
MEP-PR1-HVAC-1055 | PROC- ORDER FIN - HVAC - Thermal & Acoustic Insulation | 6 | 2025-10-13 | 2025-10-18
ELV (FAPA, VESDA,WLD, RRS & FLD) |  | 81 | 2025-09-30 | 2025-12-19
Priority 1 |  | 56 | 2025-09-30 | 2025-12-05
MEP-PR1-ELV-1005 | PROC- ORDER FIN - ELV - FAPA System | 10 | 2025-10-08 | 2025-10-18
MEP-PR1-ELV-1010 | PROC- ORDER FIN - ELV - FS Cables | 6 | 2025-09-30 | 2025-10-07
MEP-PR1-ELV-1025 | PROC- ORDER FIN - ELV - GI Conduits | 12 | 2025-11-22 | 2025-12-05
MEP-PR1-ELV-1020 | PROC- ORDER FIN - ELV - RRS | 18 | 2025-11-01 | 2025-11-21
MEP-PR1-ELV-1015 | PROC- ORDER FIN - ELV - VESDA System | 10 | 2025-10-20 | 2025-10-31
MEP-PR1-ELV-1000 | PROC- ORDER FIN - ELV - WLD & FLD System | 10 | 2025-10-08 | 2025-10-18
Priority 2 |  | 12 | 2025-12-06 | 2025-12-19
MEP-PR1-ELV-1030 | PROC- ORDER FIN - ELV - Cable Tray (Solid Trunking) | 12 | 2025-12-06 | 2025-12-19
Priority 3 |  | 0
FPS |  | 137 | 2025-09-30 | 2026-03-14
Priority 1 |  | 129 | 2025-09-30 | 2026-03-05
MEP-PR1-FPS-1065 | PROC- ORDER FIN - FPS - Automatic Purge Valve with Control Panel | 10 | 2026-01-02 | 2026-01-13
MEP-PR1-FPS-1085 | PROC- ORDER FIN - FPS - Deluge Valve | 10 | 2026-01-29 | 2026-02-09
MEP-PR1-FPS-1055 | PROC- ORDER FIN - FPS - Fire Pumps with Controller | 12 | 2025-10-07 | 2025-10-20
MEP-PR1-FPS-1015 | PROC- ORDER FIN - FPS - Fittings | 10 | 2026-02-21 | 2026-03-05
MEP-PR1-FPS-1075 | PROC- ORDER FIN - FPS - Foam Bladder Tank | 10 | 2025-11-26 | 2025-12-06
MEP-PR1-FPS-1080 | PROC- ORDER FIN - FPS - Foam Maker Nozzle with Foam Pourer | 10 | 2025-12-08 | 2025-12-18
MEP-PR1-FPS-1025 | PROC- ORDER FIN - FPS - Grooved End Vertical Trim Alarm Valve | 10 | 2025-11-03 | 2025-11-13
MEP-PR1-FPS-1095 | PROC- ORDER FIN - FPS - High Pressure Water Mist System | 12 | 2026-01-14 | 2026-01-28
MEP-PR1-FPS-1060 | PROC- ORDER FIN - FPS - Hydrant System | 10 | 2025-10-22 | 2025-11-01
MEP-PR1-FPS-1000 | PROC- ORDER FIN - FPS - Medium Velocity Water Spray System | 10 | 2026-02-10 | 2026-02-20
MEP-PR1-FPS-1090 | PROC- ORDER FIN - FPS - Open type Foam water sprinkler | 10 | 2025-12-19 | 2025-12-31
MEP-PR1-FPS-1050 | PROC- ORDER FIN - FPS - Pre Action Unit with Nitrogen Generator | 10 | 2025-11-14 | 2025-11-25
MEP-PR1-FPS-1020 | PROC- ORDER FIN - FPS - Valves (OS & Y Gate Valve, Butterfly Valve,Check Valve, Y Strainer and Auto Air Release Valve) | 5 | 2025-09-30 | 2025-10-06
Priority 2 |  | 132 | 2025-10-07 | 2026-03-14
MEP-PR1-FPS-1030 | PROC- ORDER FIN - FPS - Flow Meter | 8 | 2025-10-07 | 2025-10-15
MEP-PR1-FPS-1035 | PROC- ORDER FIN - FPS - Flow Switch | 5 | 2026-03-06 | 2026-03-11
MEP-PR1-FPS-1010 | PROC- ORDER FIN - FPS - Low VOC Paint | 3 | 2026-03-12 | 2026-03-14
MEP-PR1-FPS-1005 | PROC- ORDER FIN - FPS - MS Pipes | 5 | 2025-10-16 | 2025-10-22
Priority 3 |  | 38 | 2025-10-23 | 2025-12-05
MEP-PR1-FPS-1070 | PROC- ORDER FIN - FPS - Fire Extinguishers | 10 | 2025-11-25 | 2025-12-05
MEP-PR1-FPS-1100 | PROC- ORDER FIN - FPS - Fire Safety Signages | 10 | 2025-11-01 | 2025-11-12
MEP-PR1-FPS-1040 | PROC- ORDER FIN - FPS - Pressure Gauge | 10 | 2025-11-13 | 2025-11-24
MEP-PR1-FPS-1045 | PROC- ORDER FIN - FPS - Sprinklers | 8 | 2025-10-23 | 2025-10-31
HSD |  | 183 | 2025-09-30 | 2026-03-31
Priority 1 |  | 150 | 2025-09-30 | 2026-03-31
MEP-PR1-HSD-1100 | PROC- ORDER FIN - HSD - Automatic Decanting Station | 10 | 2026-01-06 | 2026-01-16
MEP-PR1-HSD-1040 | PROC- ORDER FIN - HSD - Basket Strainer | 10 | 2026-01-30 | 2026-02-10
MEP-PR1-HSD-1000 | PROC- ORDER FIN - HSD - Decanting Sampling Tank | 10 | 2025-12-11 | 2025-12-22
MEP-PR1-HSD-1020 | PROC- ORDER FIN - HSD - Flameproof Fusible Link Valve | 10 | 2026-01-17 | 2026-01-29
MEP-PR1-HSD-1050 | PROC- ORDER FIN - HSD - Flow Switch, Pressure Transmitter & Pressure Relief Valve | 10 | 2025-11-29 | 2025-12-10
MEP-PR1-HSD-1085 | PROC- ORDER FIN - HSD - Fuel Monitoring & Control System PLC Panels with RIO Modules | 10 | 2025-11-18 | 2025-11-28
MEP-PR1-HSD-1055 | PROC- ORDER FIN - HSD - Fuel Polishing Unit | 10 | 2026-03-07 | 2026-03-18
MEP-PR1-HSD-1015 | PROC- ORDER FIN - HSD - Fuel Transfer & Overflow Pumps | 10 | 2025-12-23 | 2026-01-05
MEP-PR1-HSD-1025 | PROC- ORDER FIN - HSD - Motorised Flameproof Valve (ON / OFF) | 10 | 2025-10-13 | 2025-10-24
MEP-PR1-HSD-1105 | PROC- ORDER FIN - HSD - MS ERW Pipes (Sch 40) | 10 | 2025-11-06 | 2025-11-17
MEP-PR1-HSD-1035 | PROC- ORDER FIN - HSD - Non Return Valve | 10 | 2025-10-25 | 2025-11-05
MEP-PR1-HSD-1010 | PROC- ORDER FIN - HSD - Overflow Tank | 10 | 2026-03-19 | 2026-03-31
MEP-PR1-HSD-1080 | PROC- ORDER FIN - HSD - Starter cum Control Panel for Pumps | 10 | 2026-02-23 | 2026-03-06
MEP-PR1-HSD-1095 | PROC- ORDER FIN - HSD - Three Piece Ball Valve | 10 | 2026-02-11 | 2026-02-21
MEP-PR1-HSD-1005 | PROC- ORDER FIN - HSD - Underground HSD Storage Tanks | 10 | 2025-09-30 | 2025-10-11
Priority 2 |  | 84 | 2025-11-06 | 2026-02-14
MEP-PR1-HSD-1045 | PROC- ORDER FIN - HSD - Auto Air Vents | 12 | 2025-11-20 | 2025-12-03
MEP-PR1-HSD-1065 | PROC- ORDER FIN - HSD - Diaphragm Solenoid Valve | 12 | 2025-12-18 | 2026-01-02
MEP-PR1-HSD-1030 | PROC- ORDER FIN - HSD - Digital Flow Meter | 12 | 2025-11-06 | 2025-11-19
MEP-PR1-HSD-1090 | PROC- ORDER FIN - HSD - Explosion Proof Local Push Button Station | 12 | 2026-01-17 | 2026-01-31
MEP-PR1-HSD-1070 | PROC- ORDER FIN - HSD - FS Cables | 12 | 2026-02-02 | 2026-02-14
MEP-PR1-HSD-1060 | PROC- ORDER FIN - HSD - Level Transmitter & Magnetic Level Switch | 12 | 2025-12-04 | 2025-12-17
MEP-PR1-HSD-1075 | PROC- ORDER FIN - HSD - Pressure Gauge & Test Point | 12 | 2026-01-03 | 2026-01-16
Priority 3 |  | 0
PHE |  | 131 | 2025-11-06 | 2026-03-16
Priority 1 |  | 108 | 2025-11-06 | 2026-03-16
MEP-PR1-PHE-1075 | PROC- ORDER FIN - PHE - CI Leaf Trap with Khurra | 2 | 2026-02-18 | 2026-02-19
MEP-PR1-PHE-1025 | PROC- ORDER FIN - PHE - CI Pipes and Fittings | 7 | 2025-11-06 | 2025-11-13
MEP-PR1-PHE-1000 | PROC- ORDER FIN - PHE - CPVC Pipes and Fittings | 5 | 2025-11-20 | 2025-11-25
MEP-PR1-PHE-1010 | PROC- ORDER FIN - PHE - DI Pipes and Fittings | 7 | 2026-01-20 | 2026-01-28
MEP-PR1-PHE-1060 | PROC- ORDER FIN - PHE - DWC Pipes and Fittings | 5 | 2026-02-06 | 2026-02-11
MEP-PR1-PHE-1005 | PROC- ORDER FIN - PHE - GI Pipes and Fittings | 5 | 2026-02-12 | 2026-02-17
MEP-PR1-PHE-1015 | PROC- ORDER FIN - PHE - HDPE Pipes and Fititings | 7 | 2026-01-29 | 2026-02-05
MEP-PR1-PHE-1055 | PROC- ORDER FIN - PHE - Lawn Hydrants | 2 | 2026-02-23 | 2026-02-24
MEP-PR1-PHE-1065 | PROC- ORDER FIN - PHE - Low Noise Pressure Pipes and Fittings | 7 | 2026-01-02 | 2026-01-09
MEP-PR1-PHE-1070 | PROC- ORDER FIN - PHE - PHE Pumps (Hydropnuematic, Submersible & Cutter) | 10 | 2025-11-26 | 2025-12-06
MEP-PR1-PHE-1040 | PROC- ORDER FIN - PHE - PRV | 8 | 2026-01-10 | 2026-01-19
MEP-PR1-PHE-1050 | PROC- ORDER FIN - PHE - Puddle Flange | 2 | 2026-02-20 | 2026-02-21
MEP-PR1-PHE-1100 | PROC- ORDER FIN - PHE - RO Plant | 8 | 2026-02-25 | 2026-03-06
MEP-PR1-PHE-1030 | PROC- ORDER FIN - PHE - SS Pipes & Fittings | 8 | 2026-03-07 | 2026-03-16
MEP-PR1-PHE-1120 | PROC- ORDER FIN - PHE - STP System | 10 | 2025-12-19 | 2025-12-31
MEP-PR1-PHE-1090 | PROC- ORDER FIN - PHE - UPVC Pipes and Fittings | 5 | 2025-11-14 | 2025-11-19
MEP-PR1-PHE-1115 | PROC- ORDER FIN - PHE - WTP System | 10 | 2025-12-08 | 2025-12-18
Priority 2 |  | 38 | 2025-12-08 | 2026-01-22
MEP-PR1-PHE-1035 | PROC- ORDER FIN - PHE - Electromagnetic Water Meter | 8 | 2025-12-26 | 2026-01-05
MEP-PR1-PHE-1045 | PROC- ORDER FIN - PHE - FRP Manhole Cover | 3 | 2026-01-06 | 2026-01-08
MEP-PR1-PHE-1085 | PROC- ORDER FIN - PHE - Grease Separators | 6 | 2026-01-16 | 2026-01-22
MEP-PR1-PHE-1080 | PROC- ORDER FIN - PHE - Oil Separators | 6 | 2026-01-09 | 2026-01-15
MEP-PR1-PHE-1110 | PROC- ORDER FIN - PHE - Sanitary Fixtures and Fittings | 10 | 2025-12-08 | 2025-12-18
MEP-PR1-PHE-1020 | PROC- ORDER FIN - PHE - Valves (Ball Valve, Butterfly Valve & Check Valve) | 5 | 2025-12-19 | 2025-12-24
Priority 3 |  | 0
BMS |  | 86 | 2025-12-11 | 2026-03-06
Priority 1 |  | 50 | 2025-12-11 | 2026-02-10
MEP-PR1-BMS-1030 | PROC- ORDER FIN - BMS - Communication Cables | 10 | 2026-01-17 | 2026-01-29
MEP-PR1-BMS-1000 | PROC- ORDER FIN - BMS - Containment System for BMS | 10 | 2025-12-23 | 2026-01-05
MEP-PR1-BMS-1025 | PROC- ORDER FIN - BMS - Fiber Optic Cables | 10 | 2026-01-06 | 2026-01-16
MEP-PR1-BMS-1040 | PROC- ORDER FIN - BMS - Network Switches | 10 | 2026-01-30 | 2026-02-10
MEP-PR1-BMS-1045 | PROC- ORDER FIN - BMS - RIO Cards & Modules | 10 | 2025-12-11 | 2025-12-22
Priority 2 |  | 60 | 2025-12-23 | 2026-03-06
MEP-PR1-BMS-1020 | PROC- ORDER FIN - BMS - BMS for Electrical Panels (PMS) | 12 | 2026-01-03 | 2026-01-16
MEP-PR1-BMS-1010 | PROC- ORDER FIN - BMS - BMS for FLD System | 8 | 2026-01-28 | 2026-02-05
MEP-PR1-BMS-1055 | PROC- ORDER FIN - BMS - BMS for TFA, PAHU's & FWU's | 8 | 2026-02-25 | 2026-03-06
MEP-PR1-BMS-1015 | PROC- ORDER FIN - BMS - BMS for WLD & PA System | 8 | 2026-02-06 | 2026-02-14
MEP-PR1-BMS-1050 | PROC- ORDER FIN - BMS - BMS for WTP & STP System | 8 | 2026-01-17 | 2026-01-27
MEP-PR1-BMS-1035 | PROC- ORDER FIN - BMS - BMS Server | 8 | 2026-02-16 | 2026-02-24
MEP-PR1-BMS-1005 | PROC- ORDER FIN - BMS - Sensors | 8 | 2025-12-23 | 2026-01-02
Priority 3 |  | 0